## Works
COAST WATER SERVICES BOARD - WORLD BANK FUNDED WATER & SANITATION SERVICE IMPROVEMENT PROJECT
PROCUREMENT PLANS - WORKS CONTRACTS
COAST WATER SERVICES BOARD - WORLD BANK FUNDED WATER & SANITATION SERVICE IMPROVEMENT PROJECT
PROCUREMENT PLANS - ADDITIONAL FINANCING- WORKS CONTRACTS
No | Contract Description | Status | Contract sum USD | Procurement Method | Review by Bank (Prior/Post) | Bidding docs & SPN to IDA | IDA No Objection to bidding docs & SPN | SPN Advert date | Bid submission & Opening | Bid opening Minutes to IDA | Submit Bid Evaluation Report (BER) to IDA | IDA No Objection to BER | Contract signature | Final Contract documents to IDA | Duration without one year Defect Liability Period
1(a) | Emergency Immediate Works-Lot 1: Agumentation of the Baricho Wellfield & Electromechanical Works | Planned | 6800000 | NCB | Post | N/A | N/A | 2015-10-05 | 2015-10-31 | N/A | N/A | N/A | 2016-01-18 | N/A | 18 months
|  | Actual | 5408061.5 | NCB | Post | N/A | N/A | 2015-07-30 | 2015-09-11 | N/A | N/A | N/A |  | N/A
1(b) | Emergency Immediate Works-Lot 2: Water Treatment/Manganese Removal | Planned | 8000000 | NCB | Post | N/A | N/A | 2015-07-01 | 2015-08-26 | N/A | N/A | N/A | 2015-10-14 | N/A | 24 months
Actual
1(c) | Emergency Immediate Works-Lot 3: Kakuyuni/Gongoni & Kakuyuni/Kilifi Interconnection Pipelines Works | Planned | 28000000 | ICB | Prior | 2015-08-29 | 2015-09-26 | 2015-10-03 | 2015-11-28 | 2015-12-05 | 2015-12-19 | 2016-01-02 | 2016-01-16 | 2016-01-23 | 24 months
|  | Actual |  | ICB | Prior | 2015-06-09 | 2015-08-07 | 2015-08-27 | 2015-10-27 | 2015-10-28
5 | Rehabilitation of the Bulk Water Pipeline System including Addendum 2 | Planned | 3600000 | NCB | Post | N/A | N/A | 2012-08-19 | 2012-09-18 | N/A | N/A | N/A | 2012-10-09 | N/A | 15 months
|  | Actual | 5961113 | NCB | Post | N/A | N/A | 2012-08-29 | 2012-10-12 | N/A | N/A | N/A | 2016-02-29 | N/A | 35 months
8 | Construction of office block for CWSB | Planned | 1100000 | NCB | Post | N/A | N/A | 2015-08-17 | 2015-09-16 | N/A | N/A | N/A | 2015-10-07 | N/A | 12 months
Actual
9 | Construction of office blocks for Tavevo and Lamu WSPs | Planned | 200000 | NCB | Post | N/A | N/A | 2012-08-29 | 2012-09-28 | N/A | N/A | N/A | 2012-10-19 | N/A | 6 months
|  | Actual | 174767 | NCB | Post | N/A | N/A | 2012-07-18 | 2012-08-15 | N/A | N/A | N/A | 2013-02-28 | N/A | Completed
10 | Rehabilitation of Kizingo WWTP | Planned | 4450000 | NCB | Post | N/A | N/A | 2015-11-30 | 2015-12-30 | N/A | N/A | N/A | 2015-11-04 | N/A | 12 months
Actual
12 | Rehabilitation of the Mombasa WSP Water Reticulation Network-Part of Lot 2 | Planned | 6000000 | NCB | Post | N/A | N/A | 2014-05-04 | 2014-06-29 | N/A | N/A | N/A | 2014-08-04 | N/A | 12 months
|  | Actual | 11490323 | NCB | Post | N/A | N/A | 2014-06-04 | 2014-07-16 | N/A | N/A | N/A | 2014-09-24 | N/A | 18 months
14 | Construction of Water Supplies in Drought Areas Lot 1: Equiping of Existing Boreholes Lot 2: Development & Equiping of New Boreholes Lot 3: Construction of Elevated Tanks at Existing Borehole Locations | Planned | 3000000 | NCB | Post | N/A | N/A | 2014-02-04 | 2014-02-04 | N/A | N/A | N/A | 2014-06-04 | 2014-06-11 | 6 months
|  | Actual | 3475230 | NCB | Post | N/A | N/A | 2014-03-03 | 2014-04-02 | N/A | N/A | N/A | 2014-07-09 | N/A | 12 months
16 | Construction of Surface Modular Pressed Steel Water Tanks for CWSB | Planned | 700000 | NCB | Post | N/A | N/A | 2013-11-30 | 2013-12-28 | N/A | N/A | N/A | 2014-01-18 | N/A | 4 months
|  | Actual | 841428 | NCB | Post | N/A | N/A | 2013-11-18 | 2013-12-17 | N/A | N/A | N/A | 2014-03-31 | N/A | 12 months
17 | Construction of earth dam in NWSB (Bute Dam) | Planned | 1200000 | NCB | Post | N/A | N/A | 2015-08-14 | 2015-09-11 | N/A | N/A | N/A | 2015-10-02 | N/A | 18 months
Actual
18(a1) | Extension/Construction of Water Supply pipelines:Lot 1 Nyalani Water Supply for Kwale County | Planned | 1000000 | NCB | Post | N/A | N/A | 2015-09-15 | 2015-10-13 | N/A | N/A | N/A | 2015-11-03 | N/A | 6 months
|  | Actual |  | NCB | Post | N/A | N/A | 2015-08-19 | 2015-09-29 | N/A | N/A | N/A |  |  | 12 months
18(a2) | Extension/Construction of Water Supply pipelines: Lot 2 Taveta Lumi W/Suppy for T/Taveta County | Planned | 1000000 | NCB | Post | N/A | N/A | 2015-07-03 | 2015-07-31 | N/A | N/A | N/A | 2015-08-21 | N/A | 6 months
|  | Actual |  | NCB | Post | N/A | N/A | 2015-07-01 | 2015-07-31 | N/A | N/A | N/A |  |  | 12 months
18(b) | Extension/Construction of Water Supply pipelines in Masalani, Moyale &Rumuruti in NWSB | Planned | 1500000 | NCB | Post | N/A | N/A | 2015-02-18 | 2015-03-18 | N/A | N/A | N/A | 2015-04-08 | N/A | 6 months
|  | Actual |  | NCB | Post | N/A | N/A | 2015-02-13 | 2015-03-16 | N/A | N/A | N/A | 2015-07-24 | N/A | 12 months
19(a) | Installation of Plastics Tanks & gutters and Fittings at Various Sites in CWSB | Planned | 200000 | NCB | Post | N/A | N/A | 2014-02-25 | 2014-03-25 | N/A | N/A | N/A | 2014-04-15 | N/A | 6 months
|  | Actual | 489280 | NCB | Post | N/A | N/A | 2014-03-10 | 2014-04-09 | N/A | N/A | N/A | 2014-07-08 | N/A | 6 months
19(b) | Installation of Plastics Tanks & gutters and Fittings at Various Sites in Wajir, Garissa & Mandera Counties in NWSB | Planned | 200000 | NCB | Post | N/A | N/A | 2014-02-27 | 2014-03-27 | N/A | N/A | N/A | 2014-04-17 | N/A | 6 months
|  | Actual | 404958 | NCB | Post | N/A | N/A | 2014-03-11 | 2014-04-10 | N/A | N/A | N/A | 2014-07-22 | N/A | 6 months
19(c) | Installation of Plastics Tanks & gutters and Fittings at Various Sites Marsabit, Isiolo Counties in NWSB | Planned | 200000 | NCB | Post | N/A | N/A | 2014-02-28 | 2014-03-28 | N/A | N/A | N/A | 2014-04-18 | N/A | 6 months
|  | Actual | 408596 | NCB | Post | N/A | N/A | 2014-03-12 | 2014-04-11 | N/A | N/A | N/A | 2014-08-07 | N/A | 6 months
20(a) | Extending services to informal settlements- Mombasa Works-Lot 1 | Planned | 1000000 | NCB | Post | N/A | N/A | 2014-04-05 | 2014-05-31 | N/A | N/A | N/A | 2014-06-21 | N/A | 9 Months
|  | Actual | 1458602 | NCB | Post | N/A | N/A | 2014-04-30 | 2014-05-29 | N/A | N/A | N/A | 2014-08-13 | N/A | 12 Months
20(b) | Extending services to informal settlements- Mombasa Works-Lot 2 | Planned | 1000000 | NCB | Post | N/A | N/A | 2014-10-05 | 2014-11-30 | N/A | N/A | N/A | 2014-12-21 | N/A | 9 Months
|  | Actual | 1689655.1724 | NCB | Post | N/A | N/A | 2014-09-12 | 2014-10-15 | N/A | N/A | N/A | 2014-12-22 | N/A | 12 Months
21 | Extending services to informal settlements- Malindi Works | Planned | 783900 | NCB | Post | N/A | N/A | 2012-09-27 | 2012-11-22 | N/A | N/A | N/A | 2012-12-13 | N/A | 9 Months
|  | Actual | 1205970.22 | NCB | Post | N/A | N/A | 2012-12-04 | 2013-01-18 | N/A | N/A | N/A | 2013-06-25 | N/A | 12 Months
22 | Rehabilitation & Partitioning of Bulk Water Company offices | Planned | 200000 | Shopping | Post | N/A | N/A | 2012-08-12 | 2012-09-09 | N/A | N/A | N/A | 2012-09-30 | N/A | 6 months
|  | Actual | 204997.33 | Shopping | Post | N/A | N/A | 2012-12-21 | 2013-01-30 | N/A | N/A | N/A | 2013-06-05 | N/A | 3 months
23 | Rehabilitation/Extension of Water Services in Tana River County (Rehab of Bura W/Supply) | Planned | 1000000 | NCB | Post | N/A | N/A | 2015-09-24 | 2015-10-22 | N/A | N/A | N/A | 2015-11-12 | N/A | 9 Months
|  | Actual |  | NCB | Post | N/A | N/A | 2015-09-23 | 2015-11-02 | N/A | N/A | N/A |  | N/A | 12 months
24 | Construction of Kilifi and Malindi Sludge Drying Beds | Planned | 500000 | NCB | Post | N/A | N/A | 2015-09-25 | 2015-10-23 | N/A | N/A | N/A | 2015-11-13 | N/A | 6 Months
Actual
25 | Kilifi NRW Works Contract | Planned | 620000 | NCB | Post | N/A | N/A | 2015-11-28 | 2015-12-28 | N/A | N/A | N/A | 2016-01-18 | N/A | 6 Months
Actual
26 | Construction of Exploratory Deep Boreholes in Tana Delta | Planned | 1450000 | NCB | Post | N/A | N/A | 2015-11-26 | 2015-12-26 | N/A | N/A | N/A | 2016-01-16 | N/A | 6 Months
Actual
27 | Rehabilitation of Hola Outstanding Works | Planned | 500000 | NCB | Post | N/A | N/A | 2016-01-25 | 2016-02-24 | N/A | N/A | N/A | 2016-03-16 | N/A | 6 Months
Actual
| Total | Planned | 74203900
| Total | Actual | 33212981.2224
format to paper
Formulas:
Contract signature = [SPN Advert date]+105
Contract signature = +[IDA No Objection to BER]+14
Bid submission & Opening = [SPN Advert date]+56
Bid submission & Opening = +[SPN Advert date]+28
IDA No Objection to bidding docs & SPN = [Bidding docs & SPN to IDA]+28
SPN Advert date = [IDA No Objection to bidding docs & SPN]+7
Bid opening Minutes to IDA = +[Bid submission & Opening]+7
N/A = +[Bid opening Minutes to IDA]+14
IDA No Objection to BER = +[N/A]+14
Final Contract documents to IDA = +[Contract signature]+7
Final Contract documents to IDA = [Contract signature]+7

## Consultancy
COAST WATER SERVICES BOARD - WORLD BANK FUNDED WATER & SANITATION SERVICE IMPROVEMENT PROJECT
PROCUREMENT PLANS - CONSULTANCY SERVICES
COAST WATER SERVICES BOARD - WORLD BANK FUNDED WATER & SANITATION SERVICE IMPROVEMENT PROJECT
ADDITIONAL FINANCING AND DROUGHT RESPONSE ACTIVITIES
PROCUREMENT PLANS -CONSULTANCY CONTRACTS
No | Contract Description | Status | Contract sum Design and Supervision USD | Procurement method | Bank Review (Prior/Post) | Submit to IDA the draft TOR, REOI | No objection by IDA on TOR | Date of EOI Advert | Date of Submission of EOI | Submission Short list to IDA | IDA No objection of Shortlist and RFP | Submission of proposals by consultants | Submission Technical Evaluation to IDA | IDA No objection of technical evaluation report | Submit combined evaluation to IDA for information | Contract Negotiation | Submit Draft negotiated contract to IDA | IDA No objection to negotiated draft contract | Contract signature | Contract Period
1(b) | Review and updating of previous studies, conceptual and detailed design, tender documents preparation and construction supervision for the emergency immediate works for lot 1,2&3 | Planned | 3000000 | QCBS | Prior | 2013-05-15 | 2013-07-17 | 2013-07-24 | 2013-08-07 | 2013-08-14 | 2013-08-21 | 2013-10-16 | 2013-10-23 | 2013-11-06 | 2013-11-27 | 2013-12-11 | 2013-12-18 | 2013-12-25 | 2014-01-08 | 36 months
|  | Actual | 3611316 | QCBS | Prior | 2012-05-24 | 2012-06-06 | 2012-06-11 | 2012-06-29 | 2012-08-13 | 2013-07-29 | 2013-09-24 | 2013-10-24 | 2013-11-26 | 2013-12-15 | 2014-01-21 | 2014-01-24 | 2014-03-27 | 2014-04-04 | 25 Months
4 | Supervision Services for the Rehabilitation of the Bulk Pipeline System Works | Planned | 850000 | SSS | Prior | N/A | N/A | N/A | N/A | N/A | N/A | 2012-10-22 | N/A | N/A | N/A | 2012-11-02 | 2012-11-09 | 2012-11-16 | 2012-11-30 | 15 months
|  | Actual | 985243 | SSS | Prior | N/A | N/A | N/A | N/A | N/A | N/A | 2012-11-14 | N/A | N/A | N/A | 2012-11-23 | 2012-12-07 | 2013-01-03 | 2013-02-01 | 15 months
5 | Energy audits in water utilities (WSPs) | Planned | 110000 | QCBS | Post | 2014-10-22 | 2014-11-05 | 2014-11-12 | 2014-11-26 | N/A | N/A | 2015-02-04 | N/A | N/A | N/A | 2015-01-11 | N/A | N/A | 2015-01-25 | 6 months
|  | Actual | 0 | QCBS | Post | 2014-07-18 | 2014-08-07 | 2014-08-14 | 2014-09-11 | N/A | N/A | 2015-02-04 | N/A | N/A | N/A | 2015-07-02 | N/A | N/A | 2015-09-15 | 6 months
6 | Customer identification survey and infrastructure mapping for all WSPs | Planned | 150000 | QCBS | Post | 2012-09-30 | 2012-10-14 | 2012-10-21 | 2012-11-04 | N/A | N/A | 2013-01-13 | N/A | N/A | N/A | 2013-05-06 | N/A | N/A | 2013-05-20 | 12 months
|  | Actual | 182319 | QCBS | Post | 2012-07-26 | 2012-08-14 | 2012-08-17 | 2012-09-04 | N/A | N/A | 2013-02-18 | N/A | N/A | N/A | 2013-08-29 | N/A | N/A | 2013-10-31 | 12 months
7 | UFW/NRW Reduction Consultancy Services for Bulk and all WSPs (Kilifi, Malindi, Lamu, Tavevo, Kwale and Tana River) | Planned | 510000 | QCBS | Post | 2015-03-30 | 2015-04-13 | 2015-04-20 | 2015-05-04 | N/A | N/A | 2015-09-11 | N/A | N/A | N/A | 2015-11-06 | N/A | N/A | 2015-12-04 | 12 months
|  | Actual | 0 | QCBS | Post | 2015-03-24 | 2015-04-21 | 2015-05-05 | 2015-05-18 | N/A | N/A | 2015-11-06 | N/A | N/A | N/A |  | N/A | N/A |  | 12 months
9 | Study on incentive based performance for Mowasco and 6WSPs Staff | Planned | 75000 | CQS | Post | 2014-05-13 | 2014-05-25 | 2014-06-01 | 2014-06-15 | N/A | N/A | 2014-08-24 | N/A | N/A | N/A | 2014-07-31 | N/A | N/A | 2014-08-14 | 4 months
|  | Actual | 156285 | CQS | Post | 2014-02-27 | 2014-05-05 | 2014-03-21 | 2014-04-04 | N/A | N/A | 2014-10-23 | N/A | N/A | N/A | 2014-12-03 | N/A | N/A | 2014-12-09 | 6 months
10 | Development of Waste water master plan for Mombasa and other selected towns | Planned | 560000 | QCBS | Prior | 2013-03-15 | 2013-08-12 | 2013-08-19 | 2013-09-02 | 2013-10-09 | 2013-10-16 | 2013-12-11 | 2013-12-18 | 2014-03-27 | 2014-04-17 | 2014-05-01 | 2014-05-08 | 2014-05-15 | 2014-05-29 | 12 months
|  | Actual | 1174407.6197 | QCBS | Prior | 2013-03-15 | 2013-07-29 | 2013-08-15 | 2013-09-02 | 2013-10-07 | 2014-11-25 | 2014-01-30 | 2014-03-13 | 2014-05-21 | 2014-06-11 | 2014-07-24 | 2014-07-31 | 2014-10-08 | 2014-10-21 | 12 months
11 | Feasibility Studies for Future Deep Ground Water Sources in Tana Delta and Msambweni Boreholes | Planned | 500000 | QCBS | Post | 2015-08-08 | 2015-08-22 | 2015-08-29 | 2015-09-12 | N/A | N/A | 2015-11-21 | N/A | N/A | N/A | 2016-01-16 | N/A | N/A | 2016-02-13 | 4 months
|  | Actual | 0
13 | Preparation/Review of strategic plans for CWSB and all the WSPs | Planned | 25000 | QCBS | Post | 2012-07-25 | 2012-08-08 | 2012-08-15 | 2012-08-22 | N/A | N/A | 2012-11-07 | N/A | N/A | N/A | 2013-04-25 | N/A | N/A | 2013-05-09 | 12 months
|  | Actual | 24800 | QCBS | Post | 2012-07-02 | 2012-09-12 | 2012-09-17 | 2012-10-03 | N/A | N/A | 2013-02-07 | N/A | N/A | N/A | 2013-07-05 | N/A | N/A | 2013-07-22 | 12 months
14 | Establishment and registration of wayleaves for water facilities for various works | Planned | 100000 | QCBS | Post | 2014-08-30 | 2014-09-13 | 2014-09-20 | 2014-09-27 | N/A | N/A | 2014-12-13 | N/A | N/A | N/A | 2014-11-19 | N/A | N/A | 2014-12-03 | 12 months
|  | Actual | 0 | QCBS | Post | 2014-10-07 | 2014-08-19 | 2014-10-28 | 2014-10-14 | N/A | N/A | 2015-04-27 | N/A | N/A | N/A | 2015-07-23 | N/A | N/A |  | 8 months
18 | Design Review & Supervision of Mombasa WSP Water Reticulation System-lot 2 | Planned | 600000 | QCBS | Prior | 2014-06-07 | 2014-06-21 | 2014-06-28 | 2014-07-12 | 2014-07-19 | 2014-07-26 | 2014-09-06 | 2014-09-13 | 2014-09-27 | 2014-10-18 | 2014-11-01 | 2014-11-08 | 2014-11-15 | 2014-11-29 | 8 months
|  | Actual | 668732 | QCBS | Prior | 2014-06-11 | 2014-06-16 | 2014-06-20 | 2014-07-07 | 2014-07-28 | 2014-08-06 | 2014-10-02 | 2014-11-03 | 2015-02-04 | 2015-02-17 | 2015-02-23 | 2015-02-23 | 2015-03-11 | 2015-03-16 | 19 months
19 | Detailed Design, Tender Document Preparation and Supervision of Kizingo WWTP | Planned | 360000 | QCBS | Prior | 2013-04-30 | 2013-07-23 | 2013-07-30 | 2013-08-13 | 2013-10-19 | 2013-10-26 | 2014-05-30 | 2014-06-06 | 2014-06-20 | 2014-07-11 | 2014-07-25 | 2014-08-01 | 2014-08-08 | 2014-08-22 | 8 months
|  | Actual | 549753.86 | QCBS | Prior | 2013-03-15 | 2013-07-29 | 2013-08-13 | 2013-08-30 | 2013-11-13 | 2013-12-09 | 2014-05-07 | 2014-08-06 | 2014-09-01 | 2014-10-23 | 2014-12-02 | 2014-12-18 | 2015-01-26 | 2015-01-30 | 24 months
21 | Drought Mitigation Study (Plan) for CWSB region | Planned | 500000 | QCBS | Prior | 2012-07-06 | 2012-07-20 | 2012-07-27 | 2012-08-10 | 2012-08-17 | 2012-08-24 | 2012-10-19 | 2013-07-15 | 2013-07-29 | 2013-08-19 | 2013-09-02 | 2013-09-09 | 2013-09-16 | 2013-09-30 | 12 months
|  | Actual | 475983 | QCBS | Prior | 2012-06-07 | 2012-06-07 | 2012-06-13 | 2012-06-28 | 2012-10-28 | 2012-10-29 | 2013-02-22 | 2013-07-15 | 2013-08-13 | 2013-09-10 | 2013-10-15 | 2013-10-22 | 2014-03-04 | 2014-04-22 | 9 months
22 | Ground Water Study for the Merti Acquifer in Wajir | Planned | 600000 | QCBS | Prior | 2013-04-30 | 2013-11-23 | 2013-11-30 | 2013-12-14 | 2013-12-21 | 2014-04-30 | 2014-06-25 | 2014-07-02 | 2014-07-16 | 2014-08-06 | 2014-08-20 | 2014-08-27 | 2014-09-03 | 2014-09-17 | 18 months
|  | Actual | 0 | QCBS | Prior | 2013-04-05 | 2014-01-22 | 2014-01-29 | 2014-02-13 | 2014-04-04 | 2014-04-30 | 2014-10-27 | 2014-12-18
23 | Supervision of Drought Response Civil works | Planned | 650000 | QCBS | Prior | 2014-01-30 | 2014-02-06 | 2014-02-13 | 2014-02-27 | 2014-03-06 | 2014-03-13 | 2014-05-08 | 2014-05-15 | 2014-05-29 | 2014-06-19 | 2014-07-03 | 2014-07-10 | 2014-07-17 | 2014-07-31 | 12 months
|  | Actual | 716010 | QCBS | Prior | 2014-02-10 | 2014-03-07 | 2014-03-21 | 2014-04-04 | 2014-05-23 | 2014-07-11 | 2014-10-21 | 2014-12-03 | 2015-03-17 | 2015-03-27 | 2015-03-31 | 2015-04-15 | 2015-04-22 | 2015-04-24 | 12 months
24 | Design Review and Supervision of Bute Dam | Planned | 685000 | QCBS | Prior | 2013-12-30 | 2014-01-13 | 2014-01-20 | 2014-02-03 | 2014-02-10 | 2014-02-17 | 2014-04-14 | 2014-04-21 | 2014-05-05 | 2014-05-26 | 2014-06-09 | 2014-06-16 | 2014-06-23 | 2015-02-15 | 18 months
|  | Actual | 1345084.9 | QCBS | Prior | 2013-12-20 | 2013-12-20 | 2014-01-13 | 2014-01-27 | 2014-03-03 | 2014-03-18 | 2014-07-24 | 2014-06-04 | 2014-11-20 | 2015-01-06 | 2014-12-11 | 2015-01-28 | 2015-02-02 | 2015-03-02 | 12 months
25 | Consultancy Services for Preparation of EIA& RAP Reports for all Works | Planned | 400000 | QCBS | Prior | 2013-10-31 | 2013-11-14 | 2013-11-21 | 2013-12-05 | 2013-12-12 | 2014-03-31 | 2014-05-26 | 2014-06-02 | 2014-06-16 | 2014-07-07 | 2014-07-21 | 2014-07-28 | 2014-08-04 | 2014-08-18 | 18 months
|  | Actual | 393835.9 | QCBS | Prior | 2013-10-29 | 2014-01-22 | 2014-01-30 | 2014-02-14 | 2014-03-19 | 2014-04-11 | 2014-06-27 | 2014-08-06 | 2014-08-29 | 2014-09-25 | 2014-09-24 | 2014-09-26 | 2014-10-28 | 2014-11-05 | 18 months
26 | Consultancy Services for Mombasa & Malindi Informal Settlements Works Supervision | Planned | 200000 | SSS | Prior | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2014-04-11 | N/A | N/A | 2015-03-15 | 18 months
|  | Actual | 0 | SSS | Prior | N/A | N/A | N/A | N/A | N/A | N/A | 2014-04-03 | N/A | N/A | N/A | 2014-04-15 | N/A | 2015-09-06 | 2015-09-10 | 30.5 months
27 | Consultancy Services for Preparation of Investment Plan for all WSPs | Planned | 550000 | QCBS | Prior | 2014-07-31 | 2014-08-14 | 2014-08-21 | 2014-09-04 | N/A | N/A | 2014-11-13 | N/A | N/A | N/A | 2015-01-08 | N/A | N/A | 2015-02-05 | 18 months
|  | Actual | 0 | QCBS | Prior | 2014-08-04 | 2014-10-02 | 2014-09-22 | 2014-10-07 | 2014-12-19 | 2014-12-30 | 2015-06-18 | 2015-08-28 | 2015-10-24
28 | Consultancy Services for Communication Strategy Contract 2 | Planned | 200000 | QCBS | Post | 2014-07-27 | 2014-08-10 | 2014-08-17 | 2014-08-31 | N/A | N/A | 2014-11-09 | N/A | N/A | N/A | 2015-01-04 | N/A | N/A | 2015-02-01 | 24 months
|  | Actual |  | QCBS | Post | 2014-08-13 | 2014-10-07 | 2014-10-27 | 2014-11-13 | N/A | N/A | 2015-03-03 | N/A | N/A | N/A | 2015-07-16 | N/A | N/A | 2015-09-28 | 24 months
29 | Consultancy for Bulk Water Services Contract 2 | Planned | 500000 | QCBS | Prior | 2014-06-26 | 2014-07-10 | 2014-07-17 | 2014-07-31 | 2014-08-07 | 2014-08-14 | 2014-10-09 | 2014-10-16 | 2014-10-30 | 2014-11-20 | 2014-12-04 | 2014-12-11 | 2014-12-18 | 2015-01-01 | 12 months
|  | Actual | 0 | QCBS | Prior | 2014-05-30 | 2014-06-01 | 2014-06-02 | 2014-07-07 | 2014-11-17 | 2015-01-28 | 2015-06-16 | 2015-09-02 | 2015-10-24 | [5 empty] | 12 months
30 | Consultancy for Implementation of the Recievables/Reconcilliation Report | Planned | 200000 | SSS | Prior | 2014-07-26 | 2014-08-09 | 2014-08-16 | 2014-08-30 | 2014-09-06 | 2014-09-13 | 2014-11-08 | 2014-11-15 | 2014-11-29 | 2014-12-20 | 2015-01-03 | 2015-01-10 | 2015-01-17 | 2015-01-31 | 4 months
|  | Actual | 230002 | SSS | Prior | 2014-08-12 | N/A | N/A | N/A | N/A | N/A | 2014-10-28 | N/A | N/A | N/A | 2014-11-06 | 2014-11-20 | 2015-02-06 | 2015-02-11 | 4 months
31 | Consultancy Services for Bute Dam Safety Inspection/Review | Planned | 300000 | QCBS | Post | 2014-07-27 | 2014-08-10 | 2014-08-17 | 2014-08-31 | N/A | N/A | 2014-11-09 | N/A | N/A | N/A | 2015-01-04 | N/A | N/A | 2015-02-01 | 16 months
|  | Actual |  | QCBS | Post | 2014-10-31 | 2014-08-16 | 2014-10-30 | 2014-11-13 | N/A | N/A | 2015-06-15 | N/A | N/A | N/A |  | N/A | N/A
32 | Supervision of Hola Lamu WSPs Works-Addendum 3 for 6WSPs Supervision | Planned | 200000 | SSS | Prior | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2015-01-11 |  |  |  | 40.5 months
|  | Actual |  | SSS | Prior | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2015-01-22 | N/A | 2015-08-21 | 2015-09-17 | 56 months
33 | Drought Mitigation Study (Plan) for NWSB region | Planned | 450000 | QCBS | Post | 2015-08-06 | 2015-08-20 | 2015-08-27 | 2015-09-10 | N/A | N/A | 2015-11-05 | N/A | N/A | N/A | 2015-12-31 | N/A | N/A | 2016-01-07 | 12months
|  | Actual |  | QCBS | Post | 2015-08-10 | 2015-08-14 | 2015-08-28 | 2015-09-10 | N/A | N/A | 2015-11-06 | N/A | N/A
| Total | Planned | 12275000
|  | Actual | 10513772.2797
Formulas:
No objection by IDA on TOR = [Submit to IDA the draft TOR, REOI]+63
No objection by IDA on TOR = +[Submit to IDA the draft TOR, REOI]+14
Date of EOI Advert = [No objection by IDA on TOR]+7
Date of EOI Advert = +[No objection by IDA on TOR]+7
Date of Submission of EOI = [Date of EOI Advert]+14
Date of Submission of EOI = +[Date of EOI Advert]+14
Submission Short list to IDA = [Date of Submission of EOI]+7
Submission Short list to IDA = [Date of Submission of EOI]+7+30
IDA No objection of Shortlist and RFP = [Submission Short list to IDA]+7
IDA No objection of Shortlist and RFP = +[Submission Short list to IDA]+7
Submission of proposals by consultants = [IDA No objection of Shortlist and RFP]+56
Submission of proposals by consultants = [Date of EOI Advert]+84
Submission Technical Evaluation to IDA = +[Submission of proposals by consultants]+7
Submission Technical Evaluation to IDA = [Submission of proposals by consultants]+7
Contract Negotiation = [Date of EOI Advert]+60
Contract Negotiation = [Submission of proposals by consultants, row below]+77
Submit Draft negotiated contract to IDA = +[Contract Negotiation]+7
Submit Draft negotiated contract to IDA = [Contract Negotiation]+7
Contract signature = [Contract Negotiation]+14
Contract signature = +[N/A]+14
N/A = +[Submission Technical Evaluation to IDA]+14
N/A = +[N/A]+21

## Goods
ADDITIONAL FINANCING AND DROUGHT RESPONSE ACTIVITIES
PROCUREMENT PLANS - GOODS CONTRACTS
No | Contract Description | Status | Contract Cost USD | Procurement Method | Bank Review (Prior/Post) | Submission of Draft Bidding Docs to IDA | IDA No objection to draft Bidding Docs | Invitation of Bids | Submission of bids & Bid opening | Submission of Bid Opening Minutes | Submission of Bid Evaluation Report (BER) to IDA | IDA No Objection Letter to BER | Review & clearance & acceptance | Issuance of letter of acceptance | Duly signed form of contract | Delilvery of Goods
1 | Supply of Bulk water equipments and tools | Planned | 350000 | NCB | Post | N/A | N/A | 2012-09-08 | 2012-10-06 | 2012-12-15 | N/A | N/A | N/A | 2013-01-08 | 2013-01-15 | 2013-03-16
|  | Actual | 1175527.39 | NCB | Post | N/A | N/A | 2012-10-15 | 2012-12-14 | 2012-12-14 | N/A | N/A | N/A | 2013-02-28 | 2013-04-15 | 2013-08-13
2 | Supply of 30,000 ordinary consumer and bulk water meters for WSPs | Planned | 1400000 | ICB | Prior | 2012-08-07 | 2012-08-14 | 2012-08-16 | 2012-09-27 | 2012-09-28 | 2012-10-12 | 2013-03-19 | 2013-03-26 | 2013-03-29 | 2013-04-05 | 2013-06-04
|  | Actual | 1624640.32 | ICB | Prior | 2012-10-03 | 2012-11-27 | 2012-12-06 | 2013-01-17 | 2013-01-18 | 2013-03-14 | 2013-04-16 | N/A | 2013-04-18 | 2013-05-13 | 2014-01-24
3 | Supply of 30 motorcycles for meter reading and general operations of the WSPs | Planned | 220000 | NCB | Post | N/A | N/A | 2012-09-13 | 2012-10-11 | 2012-10-12 | N/A | N/A | N/A | 2013-02-03 | 2013-02-10 | 2013-04-11
|  | Actual | 210988.37 | NCB | Post | N/A | N/A | 2012-09-19 | 2012-09-24 | 2012-10-24 | N/A | N/A | N/A | 2013-02-28 | 2013-04-02 | 2013-03-27
5(a) | Supply of 4No. Sets of Leak detection equipments and associated hand tools | Planned | 300000 | NCB | Post | N/A | N/A | 2013-11-12 | 2013-12-10 | 2013-12-11 | N/A | N/A | N/A | 2014-05-02 | 2014-05-09 | 2014-07-08
|  | Actual | 460967 | NCB | Post | N/A | N/A | 2014-03-03 | 2014-04-02 | 2014-04-02 | N/A | N/A | N/A | 2014-06-06 | 2014-07-04 | 2015-02-02
5(b) | Supply of 4No. Sets of Leak detection equipments and associated hand tools-rebidding | Planned | 300000 | NCB | Post | N/A | N/A | 2014-07-12 | 2014-08-09 | 2014-08-10 | N/A | N/A | N/A | 2014-09-20 | 2014-09-27 | 2014-11-26
|  | Actual | 97034 | NCB | Post | N/A | N/A | 2014-08-14 | 2014-09-10 | N/A | N/A | N/A | N/A | 2014-10-24 | 2014-11-13 | 2015-02-02
7 | Supply, Installation and Maintance of Billing Systems for 6WSPs (Malindi, Kilifi, Kwale, Tavevo, Lamu and Tana River) | Planned | 600000 | ICB | Prior | 2013-11-20 | 2013-11-27 | 2013-11-29 | 2014-01-10 | 2014-01-11 | 2014-01-25 | 2014-04-02 | 2014-04-09 | 2014-04-12 | 2014-04-19 | 2014-06-18
|  | Actual | 681877 | ICB | Prior | 2013-07-19 | 2013-11-28 | 2013-12-10 | 2014-01-21 | 2014-01-22 | 2014-03-15
8 | Supply, Installation and Maintenance of GIS Systems for 6WSPs (Malindi, Kilifi, Kwale, Tavevo, Lamu and Tana River) | Planned | 480000 | NCB | Post | N/A | N/A | 2013-10-30 | 2013-11-27 | 2013-11-28 | N/A | N/A | N/A | 2014-05-03 | 2014-05-10 | 2014-07-09
|  | Actual | 520255 | NCB | Post | N/A | N/A | 2014-01-15 | 2014-02-04 | 2014-02-04 | N/A | N/A | N/A | 2014-06-17 | 2014-07-15 | 2015-01-30
9 | Office Equipment for CWSB, Bulk Company and WSPs | Planned | 400000 | NCB | Post | N/A | N/A | 2012-10-25 | 2013-04-17 | 2013-04-18 | N/A | N/A | N/A | 2014-05-18 | 2014-05-25 | 2014-07-24
|  | Actual | 250478 | NCB | Post | N/A | N/A | 2013-03-18 | 2013-04-17 | 2013-04-17 | N/A | N/A | N/A | 2013-09-11 | 2013-10-07 | 2014-02-24
10 | Supply and Delivery of Dewatering Pumping Units | Planned | 100000 | Shopping | Post | N/A | N/A | 2015-06-30 | 2015-07-28 | 2015-07-29 | N/A | N/A | N/A | 2014-05-18 | 2014-05-25 | 2014-07-24
|  | Actual |  | Shopping | Post | N/A | N/A |  |  |  | N/A | N/A | N/A
11 | Supply of 500No. 10m3 plastic water tanks to public schools and institutions in drought prone areas for rain water harvesting | Planned | 562500 | ICB | Prior | 2012-08-16 | 2012-08-23 | 2012-08-25 | 2012-10-06 | 2012-10-07 | 2012-10-21 | 2012-10-26 | 2012-11-02 | 2012-11-05 | 2012-11-12 | 2013-01-11
|  | Actual | 522367.21 | ICB | Prior | 2012-08-17 | 2012-08-30 | 2012-09-05 | 2012-10-17 | 2012-10-18 | 2013-01-09 | 2013-04-11 | N/A | 2013-05-20 | 2013-04-16 | 2013-08-14
12(a) | Supply & Delivery of Utility Mini-lorries for CWSB, Water Bowsers and 4WD drought Monitoring vehicles for CWSB &NWSB | Planned | 1310000 | ICB | Prior | 2013-11-18 | 2013-11-25 | 2013-11-27 | 2014-01-08 | 2014-01-09 | 2014-01-23 | 2014-01-28 | 2014-02-04 | 2014-02-07 | 2014-02-14 | 2014-04-15
|  | Actual | 902228 | ICB | Prior | 2013-10-29 | 2013-11-13 | 2013-12-06 | 2014-01-17 | 2014-01-17 | 2014-04-04 | 2014-06-02 | 2014-06-06 | 2014-06-06 | 2014-07-08 | 2014-09-10
12(b) | Supply & Delivery of Portable Steel Tanks, Collapsible Tanks and Dewatering Pumps for CWSB | Planned | 450000 | NCB | Post | N/A | N/A | 2013-10-18 | 2013-11-29 | 2013-11-30 | N/A | N/A | N/A | 2014-02-18 | 2014-02-25 | 2014-04-26
|  | Actual | 163781 | NCB | Post | N/A | N/A | 2013-11-18 | 2013-12-16 | 2013-12-16 | N/A | N/A | N/A | 2014-03-05 | 2014-04-03 | 2014-10-23
13 | Supply of 9No. mobile water treatment units for both silty river water and saline water from boreholes (to be pulled by pickup) to all counties within Coast and Northern WSBs | Planned | 578500 | ICB | Prior | 2012-08-28 | 2012-09-04 | 2012-09-06 | 2012-10-18 | 2012-09-28 | 2012-10-12 | 2012-10-17 | 2012-10-24 | 2012-10-27 | 2012-11-03 | 2013-01-02
|  | Actual | 586620.36 | ICB | Prior | 2012-06-29 | 2012-08-06 | 2012-08-16 | 2012-09-27 | 2012-09-27 | 2013-01-11 | 2013-01-12 | N/A | 2013-03-26 | 2013-05-13 | 2013-08-11
14 | Supply of 2No.water trucking boats (with engine power) for Lamu and Wasini Islands | Planned | 450000 | NCB | Post | N/A | N/A | 2013-11-12 | 2013-12-10 | 2013-12-11 | N/A | N/A | 2014-01-07 | 2014-01-10 | 2014-01-17 | 2014-03-18
|  | Actual | 639192.67 | NCB | Post | N/A | N/A | 2014-05-08 | 2014-06-06 | 2014-06-06 | N/A | N/A | N/A | 2014-08-11 | 2014-10-14
15 | Supply and Delivery of Standby Generating Sets | Planned | 130000 | NCB | Post | N/A | N/A | 2014-07-08 | 2014-08-05 | 2014-08-06 | N/A | N/A | N/A | 2014-09-08 | 2014-09-15 | 2014-11-14
|  | Actual | 327696 | NCB | Post | N/A | N/A | 2014-08-14 | 2014-09-10 | N/A | N/A | N/A | N/A | 2014-10-24 | 2014-11-13
16 | Supply of submersible pumps | Planned | 150000 | NCB | Post | N/A | N/A | 2014-08-14 | 2014-09-11 | 2014-09-12 | N/A | N/A | N/A | 2014-10-14 | 2014-10-21 | 2014-12-20
|  | Actual | 40571.27 | NCB | Post | N/A | N/A | 2014-08-14 | 2014-09-11 | N/A | N/A | N/A | N/A | 2014-10-24 | 2014-11-13 | 2015-01-14
17 | Supply & Delivery of Bulk Water Machinery & Vehicles | Planned | 500000 | ICB | Prior | 2013-09-28 | 2013-10-05 | 2013-10-07 | 2013-11-18 | 2013-11-19 | 2013-12-03 | 2014-03-28 | 2014-04-04 | 2014-04-07 | 2014-04-14 | 2014-06-13
|  | Actual | 617417 | ICB | Prior | 2013-09-24 | 2013-11-13 | 2013-11-20 | 2014-01-07 | 2014-01-08 | 2014-03-12 | 2014-07-08 | 2014-07-14 | 2014-07-18 | 2014-08-14 | 2014-12-16
18 | Supply & Delivery of Bulk Water Company Office Furnishings | Planned | 100000 | NCB | Post | N/A | N/A | 2014-06-11 | 2014-07-09 | 2014-07-10 | N/A | N/A | N/A | 2014-08-08 | 2014-08-15 | 2014-10-14
|  | Actual | 99013 | NCB | Post | N/A | N/A | 2014-10-16 | 2014-11-12 | 2014-11-12 | N/A | N/A | N/A | 2014-12-18
19 | Printing of Communication Materials (Calendars, Diaries, bags etc) | Planned | 175000 | NCB | Post | N/A | N/A | 2015-09-27 | 2015-10-25 | 2015-10-26 | N/A | N/A | N/A | 2015-06-27 | 2015-07-04 | 2015-09-02
Actual
20 | Supply & Delivery of MOWASCO Repair Kit (Pipes & Fittings) | Planned | 650000 | NCB | Post | N/A | N/A | 2014-08-05 | 2014-09-16 | N/A | N/A | N/A | N/A | 2014-11-05 | 2014-11-12 | 2015-01-11
|  | Actual | 732213.6333 | NCB | Post | N/A | N/A | 2014-08-15 | 2014-09-30 | N/A | N/A | N/A | N/A | 2015-12-11 | 2015-01-30
21 | Supply and Delivery of Spare Parts for Mobile Water Treatment Units | Planned | 16000 | Shopping | Post | N/A | N/A | 2015-08-11 | 2015-08-18 | N/A | N/A | N/A | N/A | 2015-09-30 | 2015-10-07 | 2016-01-05
|  | Actual |  | Shopping | Post | N/A | N/A | 2015-08-26 | 2015-09-11
22 | Supply and Installation of Management Information Systems for 7WSPs and Bulk Water Supply Unit | Planned | 400000 | NCB | Post | N/A | N/A | 2015-09-10 | 2015-10-13 | N/A | N/A | N/A | N/A | 2015-11-05 | 2015-11-19 | 2016-03-18
|  | Actual |  | NCB | Post | N/A | N/A |  |  | N/A | N/A | N/A | N/A
| Total | Planned | 9222000
|  | Actual | 9652867.2233
Notes:
CP:19.06.07
Formulas:
Submission of bids & Bid opening = +[Invitation of Bids]+28
Submission of bids & Bid opening = [Invitation of Bids]+42
Submission of Bid Opening Minutes = [Submission of bids & Bid opening, row below]+1
Submission of Bid Opening Minutes = +[Submission of bids & Bid opening]+1
Duly signed form of contract = +[Issuance of letter of acceptance]+7
Duly signed form of contract = [Issuance of letter of acceptance]+7
Delilvery of Goods = +[Duly signed form of contract]+60
Delilvery of Goods = [Duly signed form of contract]+120
IDA No objection to draft Bidding Docs = +[Submission of Draft Bidding Docs to IDA]+7
Invitation of Bids = +[IDA No objection to draft Bidding Docs]+2
IDA No Objection Letter to BER = [N/A]+5
Review & clearance & acceptance = +[IDA No Objection Letter to BER]+7
Review & clearance & acceptance = [Submission of bids & Bid opening]+28
Issuance of letter of acceptance = +[Review & clearance & acceptance]+3
Issuance of letter of acceptance = [Submission of bids & Bid opening]+23
N/A = [Submission of Bid Opening Minutes]+14

## Training
COAST WATER SERVICES BOARD -
ALLOCATED BUDGET IN USD 700, 000 (Kshs 61,005,000 equivalent)
EXCHANGE RATE-Kshs 87.15/USD AS AT 16/08/2013
UPDATED ON 16th -April-2015
WASSIP AF TRAINING PLAN- 2014/2015
S/No | Course Description | Kshs(Planned) | USD (Planned) | Actual | No. of officers | Date of Training | Duration/ Period (Days) | Target | Location | Status | Report status
1 | Corporate governance | 700000 | 8032.1285 | 278000 | 4 | July,2014 | 5 | New Directors/Management | Mombasa | 2 Directors trained-july,2013
2 | GIS management for water utilities | 1000000 | 11474.4693 | 576776 | 5 | August,2014 | 5 | Technical staff | Nairobi | completed | report submitted-9-2-15
3 | Contract management | 1013850 | 11633.3907 |  | 2 | June,2015 | 3 | Technical staf | Nairobi
4 | customer care and Public relations | 200000 | 2294.8939 | 221400 | 5 | jan,2015 | 5 | frontline staff | Mombasa | completed
5 | IT security | 700000 | 8032.1285 |  | 2 | June,2015 | 5 | It staff | Nairobi
6 | Evaluation of tenders | 500000 | 5737.2347 | 908400 | 5 | April,2014 | 5 | Members of procurement commiittees | Nairobi | completed
7 | National HRM Conference | 200000 | 2294.8939 | 116870 | 1 | october,2013 | 5 | Hr Staff | Nairobi | completed
8 | Project planning and management | 500000 | 5737.2347 | 566600 | 4 | Feb,2014 | 4 | Staff involved in project implementation | Nairobi | completed | report submitted
9 | project monitoring and evaluation | 500000 | 5737.2347 | 575600 | 4 | Oct,2013 | 4 | Staff involved in project implementation | Nairobi | completed | report submitted
10 | Snr Management course | 624660 | 7167.642 |  | 3 | June,2015 | 30 | Management/mid management | Nairobi
11 | Team building and change management | 4350000 | 49913.9415 |  | 200 | April,2015 | 5 | All staff | VOI
12 | Environmental Planning and Implementation | 800000 | 9179.5754 | 1105138 | 1 | April,2014 | 21 | Environmental Unit | Delft, Netherlands | completed | report submitted
13 | Protocol and event management | 400000 | 4589.7877 | 476411 | 1 | July,2014 | 10 | corporate communication staff | Arusha | completed | report submitted
14 | Records management-manual and electronic | 300000 | 3442.3408 |  | 3 | may,2015 | 5 | Registry staff | Nairobi
15 | Corruption prevention in public procurement | 364379 | 4181.0557 |  | 2 | july,2015 | 14 | procurement staff, | Nairobi
16 | Advanced fraud examiners course | 350000 | 4016.0643 | 363593 | 1 | DEC,2013 | 5 | Internal Auditor | Arusha | completed
17 | Environmental management system | 685260 | 7862.9948 | 423722 | 10 | August,2013 | 2 | HOD'Sand Environmental Unit | Nairobi | completed
18 | Board and strategic leadership seminar | 764590 | 8773.2645 |  | 4 | October ,2015 | 2 | Directors | kilaguni
19 | Finance for directors seminar | 1170000 | 13425.1291 |  | 4 | May,2015 | 2 | Directors | kilaguni
20 | Directors Induction programme | 750000 | 8605.852 | 230355 | 4 | Feb,,2015 | 2 | Directors | Nairobi | completed
21 | Board and risk management | 750000 | 8605.852 |  | 4 | July,2015 | 2 | Directors | Naivasha
22 | International public sector accounting standards | 1000000 | 11474.4693 |  | 6 | June,2015 | 4 | Accounts ,Audit staff | Nairobi
23 | Conflict management | 700000 | 8032.1285 |  | 1 | Aug,2015 | 14 | HR | Kampala
24 | NWSB |  | 150000 |  |  |  |  | HOD's, Engineers and Environmental Unit
| study tour | 0 | 0 | 0
1 | study tour to US -Greenheat sanitation process | 1600074 | 18360 | 1769538 | 3 | November,2013 | 10 | Management | USA | completed | report submitted on 9-2-15
2 | Study tour to Germany | 2054114 | 23569.868 | 12423 | 4 | Feb,2015 | 5 | Management/staff | Germany
3 | Study tour to Thailand | 2400000 | 27538.7263 | 4145438 | 8 | Nov,2013 | 5 | Management/project staff | Thailand | completed | report submitted on 9-2-15
| TOTAL | 24376927 | 429712.3006 | 135057.533
TRAINING FOR WATER SERVICE PROVIDERS
(INCLUDING BULK UNIT)
S/No | Course Description
1 | Supervisory skills for supervisors and managers | 1500000 | 17211.704 |  | 10 | July,2015 | 5 | Supervisory staff | Mombasa
2 | Meter reading | 500000 | 5737.2347 | 686499 | 15 | August,2013 | 5 | meter readers | Nairobi | completed
3 | Operation and maintenance of water supply network. | 1000000 | 11474.4693 | 292000 | 10 | August,2013 | 5 | Technical staff | Nairobi | completed
4 | International public sector accounting standards | 2500000 | 28686.1733 |  | 14 | april,2015 | 5 | Accountants | Nairobi
5 | Billing and revenue collection | 1000000 | 11474.4693 | 731000 | 30 | August,2013 | 5 | Billing staff | Nairobi | completed
7 | GIS applicationin management of water utilities | 2000000 | 22948.9386 | 2480973 | 50 | Aug,2014 | 5 | Technical staff | Nairobi | completed | report submitted-9-2-15
8 | Non revenue water management | 1000000 | 11474.4693 | 1105138 | 25 | March ,2014 | 5 | Technical staff | Nairobi | completed
9 | Protocol and event management | 400000 | 4589.7877 | 465919 | 1 | July,2014 | 10 | corporate communication staff | Arusha | completed | report submitted
10 | Corporate governance | 1000000 | 11474.4693 | 1546880 | 8 | ,FEB,2015 | 5 | Directors | Mombasa | completed
11 | customer care and Public relations | 3170750 | 36382.6736 | 3149350 | 50 | Sept,2014 | 5 | Meter reading staff/front office staff | Nairobi | completed
12 | Negotiation and debt collection skills | 500000 | 5737.2347 | 884700 | 7 | April ,2014 | 5 | HR staff | Nairobi | completed
14 | career management | 1000000 | 11474.4693 |  | 8 | Sept,2015 | 10 | HR officers | mombasa
15 | Snr Management course | 1664604 | 19100.4475 |  | 8 | June,2015 | 5 | Management staff | Nairobi
16 | Records management -manual and electronic | 1000000 | 11474.4693 |  | 25 | May,2015 | 5 | Record keeping staff | Mombasa
17 | Leadership skills Development | 1500000 | 17211.704 |  | 8 | Aug,2015 | 5 | Management,mid management | Nairobi
19 | Performance management and appraissal | 2000000 | 22948.9386 |  | 10 | April,2015 | 5 | Management,supervisors | Nairobi
20 | Training on PDMA MCEmax | 2092645.8 | 24012 | 2607216 | 3 | JUNE,2014 | 10 | Engineers | Florida-USA | completed
21 | Leadership course for Africa Water Utility CEOs s | 500000 | 5737.2347 | 198292 | 2 | NOV,,2014 | 4 | Managing Directors | capetown-S.A | completed
22 | Counseling skills at workplace | 1200000 | 13769.3632 |  | 8 | July,2015 | 3 | HR managers /officers | Naivasha
23 | Finance for non finance managers | 1000000 | 11474.4693 |  | 10 | July,2015 | 5 | non finance managers | MALINDI
24 | proposal and report writing | 1500000 | 17211.704 |  | 15 | JULy,2015 | 5 | area managers | MOMBASA
25 | contract management | 2000000 | 22948.9386 |  | 11 | June ,2015 | 5 | managers | MALINDI
27 | Employee relations | 2400000 | 27538.7263 |  | 24 | August,2015 | 5 | Supervisors /mid mgt | MOMBASA
28 | Developing specifications and Bids evaluation | 1500000 | 17211.704 |  | 10 | August | 5 | tender/evaluation commiittees | NAIROBI
29 | project management | 1700000 | 19506.5978 |  | 17 | sept,2015 | 5 | Engineers /managers | NAIROBI
| study tours | 0 | 0 | 0
1 | Study tour to Nyeri water | 1000000 | 11474.4693 | 1598900 | 40 | June,2014 | 5 | Junior staff/mid Management | Nyeri | completed | report submitted 9-2-15
|  | 36627999.8 | 420286.8594 | 180686.9421
| Allocated Budget | USD | 700000
| Actuals |  | 315744.475
| Balance | USD | 384255.525

## Summary
CWSB Component - Summary of Project Costs
| As Per the Project Paper |  | 10% GoK Counterpart | Signed Finance Agreement | Signed Contracts/LPOs
| Total,US$ | IDA,US $ (Base Cost) | GoK/CWSB,US $ | Allocations US $ | Actuals/Committed US $
Works | 74203900 | 67525549 | 6678351 |  | 33212981.2224
Consuting services | 12275000 | 11170250 | 1104750 |  | 10513772.2797
Goods | 9222000 | 8392020 | 829980 |  | 9652867.2233
Training and workshops | 700000 | 700000 | 0 |  | 315744.475
Operational cost | 0 | 0 | 0 |  | 0
RAP implementation | 1500000 | 0 | 1500000 |  | 0
WaSSIP I Financing Gap | 1000000 | 1000000 | 0
Project Communication | 400000 | 400000 | 0
Drought Responses | -14007407.57 | -14007407.57 | 0
Sub Totals | 85293492.43 | 75180411.43 | 10113081 | 72594051.2 | 53695365.2005 | 73.9666 | %
Category 6 for CWSB Works, Goods, Consulancies etc including 10% unallocated |  |  |  | 58166363.2
Category 7 for CWSB& NWSB Drought Mitigation Activities including 10% unallocated |  |  |  | 14427688
Category 6 for CWSB Works, Goods, Consulancies etc excluding 10% unallocated |  |  |  | 52878512
Category 7 for CWSB& NWSB Drought Mitigation Activities excluding 10% unallocated |  |  |  | 13116080
10% Unallocated for both Category 6&7 |  |  |  | 6599459
Total |  |  |  | 72594051
[5 empty] | SDR | USD | USD
|  |  |  | Cat 6 | 38300000 | 52878512 | 58166363.2
Notes |  |  |  | Cat 7 | 9500000 | 13116080 | 14427688
1. Training and Workshops to be determined but provisional budget is USD 700,000 |  |  |  | Unallocated | 4780000 | 6599459.2
2. Operational cost to be determined |  |  |  | Totals | 52580000 | 72594051.2 | 72594051.2
3. Base cost is 90%,ie less 10% as the unallocated funds
4. NWSB Component was allocated USD |  | 10000000 and actual is 2,932,216
5. SDR exchange rate of 1.38064 of 22nd April 15

## Drought
COAST WATER SERVICES BOARD - WORLD BANK FUNDED WATER & SANITATION SERVICE IMPROVEMENT PROJECT
ADDITIONAL FINANCING AND DROUGHT RESPONSE ACTIVITIES
PROCUREMENT PLANS -CONSULTANCY CONTRACTS
NWSB Drought Subcomponent
|  | USD | Remarks
A) Works |  |  |  | Allocation Ratios as Project paper 10million against 6 million
|  |  |  | NWSB | CWSB | Totals
1) Drilling of Boreholes-Lot 4 only |  | 1360327 | Actuals
2) Bute Dam Works |  | 600000 | Planned | 10 | 6 | 16
3) Water Supplies in Masalani,Moyale &Rumuruti |  | 1991875 | Actuals | 0.625 | 0.375 | 1
4) Installation of Plastics |  | 813554 | Actuals | 9017305 | 5410383 | 14427688 | Total allocation
Subtotal 1 |  | 4765756 |  |  |  |  | as per FA
B) Consultancies
1) Merti Aquifer Study |  | 600000 | Planned
2) Supervision of Drought works |  | 358005 | Actuals
3) Design & Supervision of Bute Dam |  | 1345085 | Actuals
4) Bute Dam Safety |  | 300000 | Planned
5) Consultancy for EIAs & RAPs |  | 131278.6667 | Actuals
6) Consultancy for Drought Mitigation Study (Master Plan) |  | 450000 | Planned
Subtotal 2 |  | 3184368.6667
C) Goods
1) Supply 278 plastic tanks |  | 290436 | Actuals
2) Supply of Drought Vehicles |  | 360891 | Actuals
3) Supply of portable WTPs |  | 260720 | Actuals
Subtotal 3 |  | 912047
Grand Totals |  | 8862171.6667
NWSB Allocation |  | 9017305
Total Commitments/Planning |  | 8862171.6667
Overdrawn funds by NWSB |  | 155133.3333
CWSB Drought Subcomponent
|  | USD | Remarks
A) Works
1) Drilling of Boreholes-Lots 1,2&3 only |  | 2114903 | Actuals
2) Surface Pressed Steel Tanks |  | 841428 | Actuals
3) Nyalani Water Supply |  | 1000000 | Planned
4) Tave Lumi Water Supply |  | 1000000 | Planned
5) Bura Water Supply |  | 1000000 | Planned
6) Installation of Plastics |  | 489280 | Actuals
Subtotal 1 |  | 6445611
B) Consultancies
1) Drought Mitigation Study |  | 475983 | Actuals
2) Supervision of Drought works |  | 358005 | Actuals
3) Consultancy for EIAs & RAPs |  | 262557.3333 | Actuals
Subtotal 2 |  | 1096545.3333
C) Goods
1) Supply 278 plastic tanks |  | 231931 | Actuals
2) Supply of Drought Vehicles |  | 541337 | Actuals
3) Supply of portable WTPs |  | 325900 | Actuals
4) Supply of Collapsible & Portable Tanks |  | 163781 | Actuals
5) Supply of Water Barges/Boats |  | 639193 | Actuals
6) Supply of Standby Gensets |  | 327696 | Actuals
7) Supply of Submersible Pumps |  | 40571 | Actuals
Subtotal 3 |  | 2270409
Grand Totals |  | 9812565.3333
CWSB Allocation |  | 5410383
Total Commitments/Planning |  | 9812565.3333
Overdrawn funds by CWSB |  | -4402182.3333